## How to use
Membership Data Migration Workbook
Inventory, map, test and reconcile your member data when you switch membership software.
How to use this workbook
1. Data inventory: list every place member data lives today, who owns it, how many records and what you'll do with it.
2. Field mapping: for each field in your old system, write the new field and the rule that converts it. Get it approved before any import.
3. Validation: after each test import, enter the counts and totals from the old and new systems. Any difference is flagged automatically.
4. Cutover plan: track every task from audit to archive, with an owner and a date.
Rule of thumb: don't switch off the old system until every validation check reads Pass, and keep a read-only copy for at least 12 months.
From the Melora Connect guide: How to Switch Membership Management Software Without Losing Member Data. Vendor-neutral: use it with any platform.
Melora Connect · meloraconnect.com

## 1 Data inventory
Data inventory
Yellow cells with blue text are yours to fill. Black cells are formulas. Rows marked "Example" show the format: overwrite them.
Data type | Where it lives today | Owner | Record count | Action | Status | Notes
Member profiles and contacts | Old AMS + spreadsheet | Membership manager | 1240 | Clean, then move | In progress | Duplicates between AMS and spreadsheet
Membership types, status and renewal dates
Dues payments and receipts
Open invoices and credits
Saved payment methods / autopay
Email consent and preferences
Event registrations and attendance
Companies and linked contacts
Committees, volunteer roles and notes
Directory listings
Files and documents
Website logins / portal accounts
Tasks done |  |  | 0
Progress |  |  | 0%

## 2 Field mapping
Field mapping
Yellow cells with blue text are yours to fill. Black cells are formulas. Rows marked "Example" show the format: overwrite them.
Old system field | Example value | New system field | Conversion rule | Required? | Approved by | Status
Member Since | 03/15/2019 | Join date | Convert MM/DD/YYYY to YYYY-MM-DD | Yes | [name] | Done
Status | Grace | Membership status | Current or Grace → Active; Expired → Lapsed | Yes | [name] | In progress
Tasks done |  | 1 / 2

## 3 Validation
Validation
Yellow cells with blue text are yours to fill. Black cells are formulas. Rows marked "Example" show the format: overwrite them.
Check | Old system | New system | Difference | Result | Notes
Total member records | 1240 | 1240 | 0 | Pass
Active members
Lapsed members (last 24 months)
Members by type: [type 1]
Members by type: [type 2]
Records with a future renewal date
Dues collected, last 12 months ($)
Open invoices, total balance ($)
Email opt-outs / unsubscribed
Event registrations, last 12 months
Directory listings published
Companies with linked contacts
Checks passed | 1
Checks to investigate | 0

## 4 Cutover plan
Cutover plan
Yellow cells with blue text are yours to fill. Black cells are formulas. Rows marked "Example" show the format: overwrite them.
Phase | Task | Owner | Due date | Status
Audit | List every data source and owner (tab 1) |  |  | Not started
Audit | Export a full backup from every system |  |  | Not started
Audit | Agree what to archive instead of moving |  |  | Not started
Clean | Merge duplicate members and contacts |  |  | Not started
Clean | Fix missing or wrong renewal dates |  |  | Not started
Clean | Confirm email consent for every contact |  |  | Not started
Map | Complete the field map (tab 2) |  |  | Not started
Map | Approve the field map in writing |  |  | Not started
Test | Run test import #1 |  |  | Not started
Test | Spot-check 20 real records by hand |  |  | Not started
Test | Fill in validation (tab 3); fix and re-run |  |  | Not started
Parallel run | Process one renewal cycle or event in both systems |  |  | Not started
Parallel run | All validation checks read Pass |  |  | Not started
Cut over | Tell members what changes and when |  |  | Not started
Cut over | Ask members to re-enter saved cards if tokens can't move |  |  | Not started
Cut over | Final import and go-live |  |  | Not started
Archive | Set the old system to read-only |  |  | Not started
Archive | Keep the archive for at least 12 months |  |  | Not started
Tasks done | 0 / 18
Progress | 0%